## Sheet1
US ID# | USER STORY | TASKS | HOUR ESTIMATE | ASSIGNED TO
1 | As a reader, I want the product to be mobile, so that I can use it anywhere | Design wireframe for the application | 6 | Team (2 hours each)
|  | Setup iOS development environment | 8 | Kat
24 | As a reader, I want the view of a page to look close to the fidelity of a page in an actual book, so that it’s full story impact is maintained regardless of the medium | Design page layout | 6 | Team (2 hours each)
|  | Generate wireframe for page layout | 2 | You
|  | Write source code for page layout | 8 | Alexa
|  | Review source code for page layout | 1 | Kat
|  | Write acceptance criteria for page layout | 0.5 | Kat
|  | Write acceptance tests for page layout | 0.5 | Kat
|  | Execute acceptance tests for page layout | 1 | You
|  | Write internal documentation for page layout | 1 | Alexa
25 | As a reader, I want the background of books to be off-white (as opposed to bright-white), so that I don't strain my eyes when I'm reading | Write source code for off-white backgrounds | 0.25 | Alexa
|  | Review source code for off-white backgrounds | 0.25 | Kat
|  | Write unit tests for off-white backgrounds | 0.25 | Alexa
|  | Write acceptance criteria for off-white backgrounds | 0.25 | Kat
|  | Write acceptance tests for off-white backgrounds | 0.25 | Kat
|  | Execute acceptance tests for off-white backgrounds | 0.25 | You
26 | As a reader, I want to be able to read material without a partner, so that I can read and practice at my own pace | Write source code for solo reading | 0.5 | Alexa
|  | Review source code for solo reading | 0.5 | Kat
|  | Write unit tests for solo reading | 3 | Alexa
|  | Write acceptance criteria for solo reading | 1 | Kat
|  | Write acceptance tests for solo reading | 1 | Kat
|  | Execute acceptance tests for solo reading | 1 | You
|  | Write internal documentation for solo reading | 0.5 | Alexa
|  | Write user manual for solo reading | 0.5 | Alexa
27 | As a reader, I want the application to work in both portrait and landscape orientation, so that I can choose the way I view material | Write source code for portrait and landscape modes | 6 | Kat
|  | Review source code for portrait and landscape modes | 0.5 | Alexa
|  | Write unit tests for portrait and landscape modes | 1 | Kat
|  | Write acceptance criteria for portrait and landscape modes | 0.5 | Alexa
|  | Write acceptance tests for portrait and landscape modes | 0.5 | Alexa
|  | Execute acceptance tests for portrait and landscape modes | 0.25 | You
|  | Write internal documentation for portrait and landscape modes | 1 | Kat
28 | As a reader, I want any pictures associated with the content to appear with the text, so that they can supplement the reading material | Write source code for pictures in content | 4 | Kat
|  | Review source code for pictures in content | 1 | Alexa
|  | Write unit tests for pictures in content | 1 | Kat
|  | Write acceptance criteria for pictures in content | 0.5 | Alexa
|  | Write acceptance tests for pictures in content | 0.5 | Alexa
|  | Execute acceptance tests for pictures in content | 0.5 | You
|  | Write internal documentation for pictures in content | 1 | Kat
29 | As a reader, I want to be able to adjust font size, so that it is easier to read | Write source code for adjustable font sizes | 3 | Alexa
|  | Review source code for adjustable font sizes | 1 | Kat
|  | Write unit tests for adjustable font sizes | 1 | Alexa
|  | Write acceptance criteria for adjustable font sizes | 0.5 | Kat
|  | Write acceptance tests for adjustable font sizes | 0.5 | Kat
|  | Execute acceptance tests for adjustable font sizes | 0.5 | You
|  | Write internal documentation for adjustable font sizes | 1 | Alexa
|  | Write user manual for adjustable font sizes | 1 | Alexa
32 | As a reader, I want to be able to connect with a remote user, so that I know if I have access to someone with whom I can read | Write source code for connecting with remote user | 16 | Josh
|  | Review source code for connecting with remote user | 2 | Alexa
|  | Write unit tests for connecting with remote user | 0.5 | Josh
|  | Write acceptance criteria for connecting with remote user | 0.5 | Alexa
|  | Write acceptance tests for connecting with remote user | 1 | Alexa
|  | Execute acceptance tests for connecting with remote user | 2 | You
|  | Write internal documentation for connecting with remote user | 1 | Josh
|  | Write user manual for connecting with remote user | 1 | Josh
33 | As a reader, I want to read with a connected reader using audio, so that we can read together | Write source code for connecting with audio | 0.5 | Josh
|  | Review source code for connecting with audio | 0.5 | Alexa
|  | Write unit tests for connecting with audio | 16 | Josh
|  | Write acceptance criteria for connecting with audio | 1 | Alexa
|  | Write acceptance tests for connecting with audio | 2 | Alexa
|  | Execute acceptance tests for connecting with audio | 0.5 | You
|  | Write internal documentation for connecting with audio | 1 | Kat
|  | Write user manual for connecting with audio | 1 | Kat
|  | TOTAL HOURS | 116.75
|  |  | DEVELOPER | AVAILABLE HOURS | HOURS ASSIGNED
|  |  | Alexa | 35 | 34.5
|  |  | Josh | 40 | 39
|  |  | Kat | 40 | 35.25
|  |  | Your Tasks | - | 8