## Sheet1
US ID# | USER STORY | STORY POINTS | SCHEDULED SPRINT | SPRINT COMPLETED IN | SPRINT US WAS ADDED OR REMOVED
1 | As a reader, I want the product to be mobile, so that I can use it anywhere | 1 | 1 | 1 | Original Requirement | 90 | 1 | 20
24 | As a reader, I want the view of a page to look close to the fidelity of a page in an actual book, so that its full story impact is maintained regardless of the medium | 3 | 1 | 1 | Original Requirement | 8 | 2 | 18 | 15 | 3
25 | As a reader, I want the background of books to be off-white (as opposed to bright-white), so that I don't strain my eyes when I'm reading | 1 | 1 | 1 | Original Requirement | 82 | 3 | 16
26 | As a reader, I want to be able to read material without a partner, so that I can read and practice at my own pace | 2 | 1 | 1 | Original Requirement |  | 4 | 18 | 15 | 3
27 | As a reader, I want the application to work in both portrait and landscape orientation, so that I can choose the way I view material | 3 | 1 | 1 | Original Requirement |  | 5 | 18 | 16 | 2
28 | As a reader, I want any pictures associated with the content to appear with the text, so that they can supplement the reading material | 2 | 1 | 1 | Original Requirement
29 | As a reader, I want to be able to adjust font size, so that it is easier to read | 2 | 1 | 1 | Original Requirement
32 | As a reader, I want to be able to connect with a remote user, so that I know if I have access to someone with whom I can read | 3 | 1 | 1 | Original Requirement |  | 0 | 82 | 0
33 | As a reader, I want to read with a connected reader using audio, so that we can read together | 3 | 1 | 1 | Original Requirement |  | 1 | 62 | 20
2 | As a reader, I want the application to remotely access the book content, so that the application doesn't require a large amount of memory | 3 | 2 | 2 | Original Requirement |  | 2 | 47 | 38
3 | As a reader, I want to be able to save selected reading material locally to the device, so that I can read without a wireless connection | 3 | 2 | 2 | Original Requirement |  | 3 | 31 | 54
4 | As a reader, I want to be able to browse all available reading material, so that I can choose something to read | 2 | 2 | 2 | Original Requirement |  | 4 | 16 | 72
5 | As a reader, I want to see the covers of the books while I'm browsing through them, so that I can judge a book by its cover | 2 | 2 | 2 | Original Requirement |  | 5 | 0 | 90
6 | As a reader, I want to select reading material, so that I can read it | 2 | 2 | 2 | Original Requirement
8 | As a reader, I want to be able to search for reading material, so that I can find a specific piece of reading material that I have in mind | 3 | 2 | 2 | Original Requirement
40 | As a reader, I want my place in a book to be saved, so that I can return to that place at a later time | 3 | 2 | 2 | Added at end of Sprint 1
10 | As a reader, I want to be able to create an account, so that I can save information about my activity for my reference later | 2 | 3 | 3 | Original Requirement
11 | As an account holder, I want to be able to log into my account, so that I can access my account | 1 | 3 | 3 | Original Requirement
14 | As an account holder, I want to be able to add reading material to my To-Read list, so that I can read it later | 1 | 3 | 3 | Original Requirement
15 | As an account holder, I want to be able to delete reading material from my To-Read list, so that it is no longer found on the list | 1 | 3 | 3 | Original Requirement
16 | As an account holder, I want to be able to add reading material to my Favorites list, so that I have all my favorite reading material in one place | 0 | 3 | - | Removed at end of Sprint 3
17 | As an account holder, I want to be able to delete reading material to my Favorites list, so that it is no longer found on the list | 0 | 3 | - | Removed at end of Sprint 3
20 | As an account holder, I want to have my reading fluency and reading comprehension level tested, so that I can use it to identify appropriate reading material | 2 | 3 | 3 | Original Requirement
22 | As an account holder, I want the application to track my reading fluency and comprehension improvements, so that I can have material updated to my appropriate skill level | 3 | 3 | 3 | Original Requirement
31 | As a reader, I want to select unknown words to see their definition, so that I can learn the definition and pronunciation of new words | 3 | 3 | 3 | Original Requirement
38 | As a reader, I want to be be matched with a remote reader based on reading level, so that we both enjoy our time and feel equally challenged when reading together | 3 | 3 | 3 | Original Requirement
7 | As a reader, I want to be able to sort reading material based on comprehension difficulty or genre | 1 | 4 | - | Original Requirement
9 | As a reader, I want to be able to rate reading material, so that it can be suggested to other readers | 2 | 4 | - | Original Requirement
12 | As an account holder, I want to be able to reset my password, so that I can increase security | 1 | 4 | - | Original Requirement
13 | As an account holder, I want to be able to browse the reading material that I have previously read, so that I can go back to that content that I really liked | 3 | 4 | - | Original Requirement
18 | As an account holder, I want material suggested to me based on reading material I have rated positively, so that I can find other books that I will like | 2 | 4 | - | Original Requirement
19 | As an account holder, I want reading material suggested to me based on the other reading material I have read, so that I can easily find new reading material | 2 | 4 | - | Original Requirement
21 | As an account holder, I want reading material suggested to me based on reading level, so that it is easy to find good reading material | 3 | 4 | - | Original Requirement
23 | As a reader, I want the application to support reading fluency through voice recognition, so that the application can test reading fluency consistently and accurately | 3 | 4 | - | Original Requirement
30 | As a reader, I want pages to be animated when I turn them, so that it feels like I'm reading an actual book | 3 | 4 | - | Original Requirement
34 | As an account holder, I want to connect remotely with a friend that is also using the product, so that we can read together | 3 | 4 | - | Original Requirement
36 | As a reader, I want to be able to connect with a nearby device, so that we can read together on separate devices | 3 | 4 | - | Original Requirement
37 | As an account holder, I want to have a list of friends who also use the application, so that I can connect with them remotely to read together | 2 | 4 | - | Original Requirement
39 | As a reader, I want to read with a connected reader using video, so that I can see the person with whom I'm reading | 3 | 4 | - | Original Requirement
41 | As a reader, I want to be able to highlight text from a book, so that I can remember important aspect of the book | 1 | 4 | - | Added at end of Sprint 1
42 | As a reader, I want the highlights I created to be saved after I exit the book, so that I can review them when I return to the book | 2 | 4 | - | Added at end of Sprint 1
43 | As a reader, I want to see a synopsis page for a book that I select, so that I can determine if it is something that I want to read | 2 | 4 | - | Added at end of Sprint 2
90